General Assembly meetings

ACTIONS

| Meeting date | What? | Who? | (By) When? | Status by 29 Feb 2019 |
| --- | --- | --- | --- | --- |
|  | For next meeting/call |  |  |  |
| 190228 | Membership: Ensure signature of by-laws and governance rules by all Members | N. Francis | Mar 2019 |  |
| 190228 | Membership: Update Governance rules with agreed Associate association membership conditions and circulate for signature by all Members | C. Braibant | Mar 2019 |  |
| 180405 | Membership: Approach American partners to organize an Antimony Day America | N. Francis | Q3 2018 | On-going, Washington 5 Apr 2019 |
| 190228 | Membership: Participate in events in Asia only when travel and accommodation costs are sponsored | C. Braibant | China: Jun 2019 Japan: Oct-Nov 2019 |  |
| 190228 | Regulatory: Inform i2a about cases of deviations from i2a’s self-classifications for Sb substances on the market | Members | ASAP |  |
| 190228 | Regulatory: Chase NTP to obtain clarification on scope and timing of RoC Listing of ATO | C. Braibant | Mar 2019 |  |
| 190228 | Regulatory: Chase ECHA to obtain specific week/day of release of draft SEv decisions | C. Braibant | Mar 2019 |  |
| 190228 | Regulatory: Mobilize attention of Commission on RoHS project to avoid useless/damaging results | C. Braibant (with BSEF, EM and cefic) | Mar 2019 |  |
| 190228 | Regulatory: Send all recent, reliable and relevant data for risk assessment to Environment Canada and Health Canada | C. Braibant | Mar 2019 |  |
| 181115 | Regulatory: Produce dedicated risk/benefit description of participating/not participating in i2a’s Workplace Exposure Monitoring Campaign | C. Braibant | ASAP | On-going |
| 190228 | Regulatory: Produce comment to draft TLV proposal from ACGIH (and include request for clarification of TLV calculation, and note on LoD/LoQ / sample duration vs activity duration) | C. Braibant, C. Boreiko | 31 May 2019 |  |
| 171130 180405 180626 | Regulatory: Commission SEA study to quantify societal value of Sb substances, and subsequently: - Relative value/benefits of Sb vs other metals - Costs triggered by a reclassification (or RoHS restriction) - Quantification of trade-off between chemical risk and fire safety | C. Braibant | 13-14 Nov 2018 | On-going |
| 190228 | Budget: Circulate/Complete membership tonnage questionnaire | N. Francis/Members | Mar 2019 |  |
| 181115 | Budget: Revise LoA itemization/fee justification and reimbursement/reinvoicing calculations upon final 2018 expenses | C. Braibant / Treasurer / Board | Mar 2019 |  |
| 190228 | Communication: Provide comments on Communication Plan | Members | 15 Mar 2019 |  |
| 190228 | Communication: Circulate overview of regulatory landscape around Sb substances | C. Braibant | Mar 2019 |  |
| 190228 | Communication: Comment progress tracking tool | Members | On-going |  |
| 190228 | Communication: Circulate Save the date announcement for 2019 Sb Day | N. Francis | < 15 Mar 2019 |  |
|  | For Q2 2019 |  |  |  |
| 181115 | Based on revised LoA itemization/fee justification and reimbursement/reinvoicing calculations upon final 2018 expenses, and first draft SEv decision, determine and distribute predicted SEv costs across all Sb substances registrants and decide whether/when to invoice SEv to non-i2a Members | C. Braibant /Treasurer / Board | < Jun 2019 |  |
|  | For End 2019 |  |  |  |
| 181115 | Agree on which/how workplace exposure data collected during i2a’s Workplace Exposure Monitoring Campaign will be reported to authorities | C. Braibant/EHS Group/Board | End 2019 |  |
| 190228 | Check success of Associate Association membership and decide whether to retain or adjust | Board | End 2019 |  |