Strategy for the resilience of the Antimony sector as from 2018

Brussels, 10 September 2018

Version 1.2

| Version | Section | Change | Reason |
| --- | --- | --- | --- |
| 1., 15 March 2018 |  |  | First version approved by Board and General Assembly |
| 1.1, 21 June 2018 | 4 | Addition of STOT RE and reproductive toxicity concern | Requested by BAuA as part of Substance Evaluation |
|  | 6.1 | Reordering of Table 2 and addition of in vivo studies for reproductive toxicity | Anticipation of likely request for an EOGRTS by BAuA as a result of Substance Evaluation |
| 1.2, 10 September 2018 | 6.1 | Update of Table 2 (format and content) Addition of in vivo studies for genotoxicity | Better reflect objective of each work item and ‘types’ of work items included in the plan Ensure robust interpretation of NTP carcinogenicity results and subsequent BAuA’s proposed CLH |
|  | 6.2 | Addition of ‘advocacy’ dimension in communication plan | Evidence and materials generated by i2a will initially be communicated and then become advocacy tools |
|  | 6.3 | Addition of task forces and Communication expert in human resources plan | Allow specialized input to work on i2a deliverables |

Contents

1.	Purpose of this document	3

2.	The Antimony world	3

3.	The perceived image of Sb	4

4.	Regulatory scrutiny on Sb	5

5.	The vision, mission/mandate and strategic objectives of i2a	7

6.	Strategy to address issues influencing the perceived image of and regulatory scrutiny on Sb	7

6.1	Technical plan	9

6.2	Communication and advocacy plan	13

6.3	Human resource plan	14

6.4	Funding plan	16

7.	References	17

Annex 1 – Practical consequences of the (re-)classification of antimony trioxide (and other Sb substances)	18

Annex 2 – Synopsis of i2a’s Strategy for 2018-2025	19

Annex 3 – Job descriptions of i2a officers	21

Annex 4 – i2a Expanded networking organizational structure	25

# Purpose of this document

The Sb sector is facing a major regulatory scrutiny.  Compared to previous regulatory attention (ATO-specific, cancer-specific, EU-specific), the one taking place today covers all Sb substances, cancer, developmental and cardiac issues, and has an international scope.  During this scrutiny, it is important to address both the regulatory processes and the perceived image of Sb.  This requires a revamped and common view and approach by all i2a Members on the technical, communication/advocacy, resource and financial requirements to be centralized within i2a.  This living document aims to describe i2a’s strategy for 2018-2025.

# The Antimony world

World Sb resources have been estimated at 5 million tons in 2011 by Bio Intelligence Service (2015).  According to USGS, world Sb reserves amounts 2 million tons, of which 80% is concentrated in three countries (China (48%), Russia (18%) and Bolivia (16%) (USGS, 2016).

The annual world mine production of Sb is about 175,500 tons (BGS, 2015), of which 86% is extracted from China (78%), Russia (4%), and Tajikistan (4%).  Sb is furthermore a co- or by-product of the production of Au, Pb, Cu and Zn.

Major global end uses of Sb include: Flame retardants, Lead-acid batteries, and Lead alloys (cf. Figure 1).  Other sectors also depending on Sb substances include: PET, polyester, PVC, technology glass, pigments, ceramics and enamels, and pyrotechnic.

Figure 1: Global consumption/end uses of Sb (Roskill, 2014)

In all applications, only relatively small quantities of Sb are needed to achieve the required function.  But even in such small quantities, Sb enables the availability and performance of significant quantities of articles which are indispensable to society: flame retardant textiles, heat-stable plastics (43 million tons in 2015 (PlasticsEurope, 2016), PET resin (27.8 million tons in 2015 (PlasticsInsights, 2016), polyester textile, lead-based batteries (demand of 478 million KVAh in 2014 (PR Newswire, 2016)), lead-based alloys, high purity and transmission flat glass (global photovoltaic glass consumption attained 580 million m² in 2015 (Globe Newswire, 2017)), to name only a few.

Secondary Sb is mainly only recovered from spent lead-acid batteries.  Sb used in the manufacture of plastics and flame retardants is generally not recovered because Sb is dispersed in these products (Schwarz-Schampera, 2014).  Sb could potentially be recovered from the bottom ash resulting from the incineration of some of these end products at the end of their life, if this process can be made economically viable.  This will be closely related to the increasing flame retardancy and PET markets.

The diagram below (Figure 2) summarizes the stakeholders who have expectations related to Antimony (Sb) substances, and which are to be considered/should be involved in all i2a initiatives:

Figure 2. The Antimony world

# The perceived image of Sb

A number of reasons may make stakeholders believe in the performance and safety of Sb substances, or alternatively, believe that Sb substances are not the best choice of substance.

A quick internet search on antimony uses will typically put forward the role of Sb substances in flame retardancy and sustainable lead applications, as well as in critical medical applications, and high-tech semiconductor devices.  This image is however also downgraded by several publications on its health and environmental impacts.

The perceived image of Sb is reported in a brief and comparative manner in Table 1 below.  Each aspect of Sb’s image has a positive and a negative side, depending on the point of view.

Table 1. Perception of Sb by supportive and skeptical stakeholders

|  | Why Sb? | Why not Sb? |
| --- | --- | --- |
|  | Not scarce, sufficient reserves in the world compared to demand | High dependence on Chinese providers and other controversial territories (responsible sourcing questioned) |
|  | Extracted as a by-product of gold mining, maximizes efficiency of extraction of scarce material | Also associated to environmental releases of Pb and As which co-exist with Sb in some mines |
|  | Good price, good value for money | Volatile pricing |
|  | Multi-function, versatile (can be used in many physical and chemical forms), relatively small quantities needed | - Dispersed presence in many articles - Contributes to continued used of Brominated flame retardants, Pb, PVC, PET, and other environmentally non-friendly materials |
|  | Despite being a (heavy) metalloid, it is relatively inert | - Associated to lung cancer, increase in spontaneous miscarriages, dermal irritation and other organ-specific toxicities, as well as autism - Undocumented workplace and consumer exposure |
|  | Makes applications more resource efficient (synergist: less brominated flame retardant needed to reach same performance, better throughput and quality of PET catalysis) | Contributes to applications which are not strictly necessary (e.g. flame retardancy used beyond strict industrial and professional needs) |
|  | Recyclable, contributes to Circular Economy goals | Recycling beyond metallic applications not sufficiently explored/ensured |
|  | Not controversial, relatively low on authorities’ radar screen | Could become more controversial if above issues are not addressed, regulatory pressure is generally increasing worldwide |

# Regulatory scrutiny on Sb

The release of the draft report of the NTP 2-year inhalation carcinogenicity studies on antimony trioxide, triggered a renewed attention on Sb substances.  This study reports some evidence of cancer in rats and clear evidence of cancer in mice.  The evidence adds up to the previous animal toxicity studies and challenges the existing classification of antimony trioxide as a suspected carcinogen (GHS/CLP category 2).  Authorities consider that the carcinogenicity potential of antimony trioxide is now presumed (GHS/CLP category 1B), and the potential for other Sb substances to pose a similar concern is under discussion too.  The possible (re-)classification scenarios are outlined in Figure 3 below.  The practical impacts are described in more detail in Annex 1.

Beyond the carcinogenicity classification, evidence has prompted an additional classification as Specific Target Organ Toxicity (STOT) upon Repeated Exposure (RE).  Industry added a STOT RE 2 self-classification for the relevant Sb substances in 2018.

Authorities also question the possible reproductive toxicity and endocrine disrupting properties of Sb substances.  This may trigger further testing needs and/or an additional classification of Sb substances.

The STOT RE and a possible reproductive classification need to be addressed in conjunction with any possible stricter (re-)classification of antimony trioxide and other Sb substances for carcinogenicity.  These will lead to a number of consequences, among which the need to update existing risk assessments and impose measures to reduce exposure in workplaces, and presence in/release from consumer articles.  In this context, it is important for i2a to work on the sustainability profile of Sb substances, as they will increasingly compete with “safer” alternatives.

Figure 3. Possible antimony trioxide (and other Sb substances) (re-)classification scenarios

# The vision, mission/mandate and strategic objectives of i2a

i2a Vision: a sustainable and responsible Sb industry, where Sb substances continue to be the material of choice for many technology-enabling applications.

i2a Mission/Mandate: to ensure the safe use of Sb substances, in other words, the responsible management of Sb substances throughout their lifecycle.  A comprehensive concept to describe this is product stewardship.  The mandate and role of i2a is to inspire product stewardship along the Sb value chain, from classification to sustainability profiling.

i2a Strategic objectives:

- Address knowledge gaps weakening the safe use and positive image of Sb substances

- Ensure that the most up to date evidence is used in any regulatory scrutiny of Sb substances

- Determine the most relevant, proportionate, and efficient risk management measures applicable for each use of Sb substances

- Support the Sb industry in implementing responsible product stewardship practices

# Strategy to address issues influencing the perceived image of and regulatory scrutiny on Sb

Members expect i2a to strengthen the “why” and to tackle the “why not” of the perceived image of Sb described in Table 1.  Adverse health effects and exposure risks which yield EHS regulatory requirements and questioning around Sb substances for all stakeholders in the Sb world fall directly within the mandate of i2a.  In the immediate term, i2a should hence improve the perceived image of Sb on these classification and risk assessment aspects.

Where concerns or risks remain, i2a should work towards the identification of the most efficient measures to tackle this via a Risk Management Option Analysis (RMOA).  This requires the proper identification of the downstream sectors where the use of Sb substances can be done/continued safely, where applicable risk management measures are implemented.  This will enable to more robustly benchmark Sb substances against other substances potentially used for similar applications.

The timeline of this strategy will be dictated by the EU Evaluation processes (and parallel US developments) which will commence in 2018, and probably followed by a final decision around two years later, i.e. by end 2020.  The output of this strategy will address and hence be useful for EHS regulatory processes beyond 2020, probably deployed between 2020 and 2025.

The Strategy will be composed of four specific plans:

- A technical plan

- A communication and advocacy plan

- A human resource plan

- A funding plan

Annex 2 explains why the strategy and the related investment must be deployed rather earlier (anticipate) than later (wait and see mode).  The triggers, scope and timeline of the strategy are summarized in Figure 4 below.

Figure 4. Overview of the regulatory work to be implemented by i2a

## Technical plan

The initial scientific work conducted on Sb substances aimed to generate information necessary to populate a minimum database on Sb substances and judge on the possible health effects which could be caused by Sb substances.  This included animal test data, workplace exposure data, and read-across supporting evidence, mainly.  This first phase of work was concluded with the evidence gathered in the format of EU REACH Registration Dossiers, which contains the risk characterization and classification for the various Sb substances.

Since then, recent research has yielded additional evidence on health effects apparently attributed to exposure to Sb substances.  In particular:

- The US NTP 2-years inhalation carcinogenicity studies on antimony trioxide (and the associated mutagenicity/genotoxicity assessment)

- A number of publications having pointed towards the possible toxicity to reproduction and heart of Sb-drugs administered to patients with leishmaniosis

The above reopens the discussion on the classification of Sb substances, and the grouping and read-across approach around four endpoints of concern:

- Lung toxicity and carcinogenicity

- Genotoxicity

- Reproductive toxicity

- Cardiotoxicity

As regards cardiotoxicity, it is of relatively lower concern than the other endpoints, and is not prioritized in the work of i2a.

In addition to updating the toxicity effect, mode of action and read-across assessment, the additional evidence prompts the revision of existing classifications (including transport classification) and ‘safe levels’.  The latter requires updated exposure datasets to determine whether recent exposure levels occur at or below these lower ‘safe levels’.  Exposure data is needed both from workplace (industrial and professional) and consumer products (releasing Sb during use or at end of life).

The technical plan set-up by the i2a EHS Group to tackle the additional evidence and its scientific, technical and regulatory consequences is described in Table 2 below.

Table 2. Work items to address research questions and regulatory proposals around mode of action, hazard, classification, and exposure assessment of Sb substances

|  | Work item | Content | Objective | Regulatory process the work item contributes to |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Classification and risk assessment |  |  | Read-across | Restrictions | TLV / OEL |
|  |  |  |  | Lung toxicity / Carcinogenicity | Genotoxicity | Reproductive toxicity |  |  |  |
|  | Desk work (lead by i2a Secretariat and expert consultants) |  |  |  |  |  |  |  |  |
|  | - Scientific opinions | A summary of conclusions that can be made on the basis of the available toxicological evidence, and further research opportunities for each endpoint of concern for Sb substances. | To facilitate communication about the scientific opinion and research plans of i2a on each endpoint of concern. | X | X | X | X |  |  |
|  | - Scientific publications | Peer reviewed publications in scientific journals, of evidence to be considered by the scientific and regulatory communities interested in Sb substances. | To promote the use of i2a’s evidence and interpretation / conclusions by the scientific and regulatory communities. | X | X | X | X |  |  |
|  | - Scientific review of preceding cases | Review of other substances having undergone REACH and/or CLP (or OEL) processes similar to those of relevance for Sb substances. | To extract learning lessons to be considered in the technical plan for Sb substances. | X | X | X | X | X | X |
|  | - (Q)SAR model | Model to compare and predict effects of substances based on structural similarity. | To be used in building read-across justification for Sb substances. | X | X | X | X |  |  |
|  | Laboratory work (lead by test houses and expert consultants) |  |  |  |  |  |  |  |  |
|  | - Quantifica-tion and speciation method | Validation of the sampling and analytical methods used in any study to determine or speciate Sb in any sample. | To increase the reliability of any study performed by i2a. | X | X | X |  | X | X |
|  | - Solubility and bio-accessibility study | Generation of solubility and bio-accessibility data for all Sb substances. | To compare and rank/group Sb substances and: identify most relevant test items for further in vivo tests, and build read-across justification for Sb substances. | X | X | X | X |  |  |
|  | - In vitro inhalation toxicity study | In vitro replication of in vivo lung conditions and inhalation exposure to Sb substances. | To compare and rank/group lung toxicity effects of all Sb substances and: identify most relevant test items for further in vivo tests, further build read-across justification for Sb substances, and determine applicable classification for each Sb substance. | X | X |  | X |  |  |
|  | - In vivo genotoxicity studies | In vivo studies to assess genotoxicity of Sb substances. | To clarify outstanding questions in carcinogenicity results of NTP study, and determine applicable mode of action and resulting classification of Sb substances. | X | X |  |  |  |  |
|  | - In vivo reproduc-tive toxicity studies | In vivo studies to assess the possible reproductive toxicity of Sb substances. | To clarify interpretation of adverse effects observed in various reproductive studies with Sb substances, inform the design of a cost-efficient and tailored EOGRTS study, and satisfy the mandatory EOGRTS testing proposal requirement in REACH. |  |  | X |  |  |  |
|  | Field work (lead by expert consultants and companies) |  |  |  |  |  |  |  |  |
|  | - Workplace PSD, air and biomonito-ring program | Harmonized and coordinated campaign to collect measured data about Sb in workplace air and in relevant biological fluids and health surveillance programs. | To avoid a precautionary overestimation of exposure and use of conservative assessment factors in exposure limit calculations, and to inform on best practice to monitor workplace exposure. | X |  |  |  | X | X |
|  | - Socio-economic analysis of regulatory proposals | Assessment of societal benefits of Sb substances and socio-economic impacts of regulatory proposals and decisions. | To reinforce perceived value of Sb substances, and balance decision-making towards positive cost-benefit measures. | X | X | X |  | X | X |

## Communication and advocacy plan

The communication and advocacy plan will be developed with the i2a Communication Group.  i2a’s main communication tools are its mails, newsletters, website, developing social media exposure, and its annual internal and open events.  The Communication Group will be in charge of setting-up the suitable mix of tools to ensure proper information and involvement of Members and outreach towards potential Members and other stakeholders.  Reaching out to the authorities among these stakeholders may take the form of advocacy in due course.

As regards Communication to i2a Members, Table 3.1 presents how the different tools should be used.  Mails shall be used only when an action is required.  Other tools shall be used to inform Members.

Table 3.1 Purpose, frequency and format of i2a internal communication tools

| Tool | Main purpose |  | Frequency | Format |
| --- | --- | --- | --- | --- |
|  | Action | Information |  |  |
| Mail | X |  | Ad hoc | Max 2 paragraphs Short background/objective Description of action Deadline Level of urgency marked with color-code - Red = very urgent (< week) - Orange = urgent (< 3 weeks) |
| Newsletter |  | X | Trimonthly: Mar, Jun, Sept, Dec | Max 2 pages + Acronyms Welcome words Sb EHS regulatory horizon i2a’s Product Stewardship Strategy i2a Networking & Partnership i2a Public events i2a Internal meetings Article recommended by the Chairs i2a Website and Social Media Activity |
| Annual Report |  | X | Annual: Jun or Dec | Max 10 pages Recap of Vision, Mission, and strategic objectives Progress against technical, communication, human resource and funding plans General achievements |
| Members-only section of website |  | X | Monthly review / update | Work in progress |

As regards Communication to reach out to potential Members and other stakeholders, Table 3.2 presents how the different tools should be used.  None of these involve any advocacy-type of communication, as advocacy requires other approaches and tools.

Table 3.2. Purpose, frequency and format of i2a outreach communication

| Tool | Main purpose |  | Frequency | Format |
| --- | --- | --- | --- | --- |
|  | Information | Visibility |  |  |
| Public website | X | X | Monthly review / update | Work in progress |
| Social media |  | X | At least 1/week | Max 5 lines Topical message or question Reference to i2a Relevant photo and/or link |
| Technical workshop | X |  | Annual | 1 day max Specific technical issue Presentations, break-out groups, and training |
| Event | X | X | Annual: Nov | 1 or 2-days Specific question / objective / audience Moderator and cartoonist / infographics Market trends, regulatory trends, and i2a Product Stewardship initiative Presentations, panel, breakout groups, and interview |

## Human resource plan

The technical and communication/advicacy plan require human resources to be implemented.  The expertise needed are: administration, project management, toxicology, occupational medicine and hygiene, communication, advocacy, among others.  The ideal composition of the i2a Secretariat is: a Secretary-General, an Office and Communication Manager, and a Regulatory Toxicologist (cf. Job descriptions in Annex 3).

The in-house expertise needs to be completed with:

- external service providers

- i2a Members

- associations i2a is a Member of

- network of Sb value chain

External support is needed from experts in specific toxicological endpoints (e.g. carcinogenicity and genotoxicity), hazard assessment, exposure assessment (and related models), IUCLID and related softwares, in vitro testing, in vivo testing, and workplace (bio-)monitoring.  This external support will be covered by the relevant i2a annual budgets and the Secretary-General should be given discretionary power to maneuver within this human resource needs and agreed budgets, with the collaboration of the Treasurer of i2a.  The Board shall regularly reappraise the level of human resources needed.

Associations i2a is a member of, as well as the broader network of contacts of i2a, are also key to succeed in addressing i2a’s strategic objectives.  Advocacy bodies should provide the relevant political support to i2a.  Downstream users of Sb are the best porte-paroles of the continued use of Sb, and the only ones able to inform about the exposure potential associated to the various uses.  Figure 5 displays the organizational membership structure of i2a.  The expanded network of i2a is available in Annex 4.

Figure 5. i2a Membership organizational structure

## Funding plan

i2a’s actions must be implemented in a transparent and efficient manner to enable the smooth involvement of as many stakeholders as possible in the scientific and regulatory process affecting Sb substances.

It is essential to:

- Retain the current membership, which is composed primarily of EU producers and EU traders, who share the cost of i2a’s programs and administrative support according to a cost-sharing formula based on cumulative tonnages of all Sb substances produced or traded by each company worldwide; and

- Increase the membership, in particular to ensure a better geographical and value chain coverage, and to obtain the necessary financial support, representation and leverage, and expertise and evidence to address the remaining questions; and

- Ensure the collaboration and participation of the mining and downstream user companies. Because these downstream user sectors depend on Sb to succeed in their multiple applications, and the miners depend on the success of this continued use, they should both be more actively involved in the addressing the knowledge gaps around the safety of Sb substances.

The Board shall regularly reappraise the membership spread versus the level of human resources available.   Before approaching any potential new member, it is important to understand their expectations and whether i2a can truly meet these.

When membership does not appear to be a viable option, i2a should make sure that a collaborative approach is used that ensures responsibility of a number of tasks with e.g. upstream or downstream associations or companies.  The priority of i2a should be that all segments of the value chain address the information needs pertinent to their specific role in the Sb value chain.

Free-riding should be discouraged and legal action taken when applicable.  In order to raise awareness on the information needs at international level and work against free-riding, i2a can offer to participate in one event per year in America and Asia, with travelling costs covered by the local hosts.

Funding of i2a’ work program and outreach activities will be ensured by:

- Membership incomes;

- Selling of hazard and exposure data for EU-REACH and similar regulations worldwide;

- Sponsoring of international presentations; and

- Organization of technical workshops and annual Antimony Days.

As regards i2a technical workshops and annual Antimony Days:

- Participation fees for non-Members should always be decided by the Board, in order to attract participation while compensating for i2a’s expenses in organizing these value chain beneficial events;

- Sponsorship should be stimulated for any i2a event as a way to alleviate the cost for i2a;

- To the extent that co-organizers can bring added value to an event, co-organization should be considered where possible, so as to share the costs of the events with the value chain.

# References

BGS (2016).  World Mineral Production 2010-2014 [online].  Keyworth, Nottingham British Geological Survey.  Available at: http://www.bgs.ac.uk/mineralsuk/statistics/home.html.

Bio Intelligence Service (2015).  Study on Data for a Raw Material System Analysis: Roadmap and Test of the Fully Operational MSA for Raw Materials – Final Report.  Prepared for the European Commission, DG GROW.

Globe Newswire (2017).  Global and China Photovoltaic Glass Industry Report 2016 - 5 Global and 18 Chinese PV Glass Companies.  Research and Markets, Globe Newswire [online].  Available at: https://globenewswire.com/news-release/2016/08/03/861195/0/en/Global-and-China-Photovoltaic-Glass-Industry-Report-2016-5-Global-and-18-Chinese-PV-Glass-Companies.html.

PlasticsEurope (2016).  World Plastics Materials Demand 2015 by Types.  PlasticsEurope Market Research Group (PEMRG) / Consultic Marketing & Industrieberatung GmbH [online].  Available at: https://committee.iso.org/files/live/sites/tc61/files/The%20Plastic%20Industry%20Berlin%20Aug%202016%20-%20Copy.pdf.

PlasticsInsights (2016).  Global PET Resin Production Capacity.  Editorial Team in Material Market, Plastics Insights [online]: Available at: https://www.plasticsinsight.com/global-pet-resin-production-capacity/.

PRNewswire (2016).  Global and China Lead-acid Battery Industry Report, 2015-2018 [online].  Available at: http://www.prnewswire.com/news-releases/global-and-china-lead-acid-battery-industry-report-2015-2018-300200529.html.

Roskill (2014). Sb: Global Industry, Markets & Outlook [online].  Available at: https://roskill.com/market-report/Sb/.

Schwarz-Schampera, U. (2014).  Sb.  In: Gunn, G. (Editor), Critical Metals Handbook, John Wiley & Sons, 70-98.

USGS (2016).  Mineral Commodity Summary.  Sb [online].  Available at: https://minerals.usgs.gov/minerals/pubs/commodity/Sb.

# Annex 1 – Practical consequences of the (re-)classification of antimony trioxide (and other Sb substances)

# Annex 2 – Synopsis of i2a’s Strategy for 2018-2025

# Annex 3 – Job descriptions of i2a officers

Secretary-General

Responsible for representing the International Antimony Association (i2a), as well as for overseeing the projects (and associated budgets) of i2a, while guarding the application of the i2a’s By-laws and related documents, within the boundaries of Competition Law and confidentiality.

The Secretary-General reports to the Chairman and Co-Chairman of i2a and serves the interests of the association and all its projects.  All officers and consultants working for i2a report to the Secretary-General.  The Secretary-General acts as back-up for the other officers of i2a when needed.

The main responsibilities of i2a’s Secretary-General, supported by relevant external experts and those of i2a, are:

- Prime contact and representative of i2a for Members, potential members, other associations, and third parties including research institutions, governmental and non-governmental organisations, public and political authorities, etc.

- Secretariat for i2a’s General Assembly and Board of Directors: Preparation of agenda, background material (e.g.: budget, presentations, organisation/(co-)funding of i2a projects), and minutes; and follow-up of all related action points

- Accountable for i2a’s administrative matters: preparation of i2a statements and publications; under the guidance of the Treasurer of i2a, act as co-signature authority on behalf of i2a for e.g.: approval of invoices, quotations, contracts, study plans, proposals, etc.; preparation, evaluation and signature of contracts and contractual agreements with third parties

- Supervision, coordination and support of i2a officers and service providers

- Representation of i2a in associations/structures i2a is a member of, including e.g.:

  - International Council on Mining and Metals (ICMM): Chemicals Management WG, and Life-Cycle Management WG

  - Eurometaux: Assembly, relevant EHS and REACH groups.  Co-Chair of REACH data-sharing Task Force.  RoHS Coordination point

  - Critical Raw Materials Alliance (CRM Alliance): General Assembly, CRM Day, Special Actions

  - Cross-Industry Initiative on better regulation for chemicals management: Strategy Group, Chair of Substitution Work Group

  - North American Metals Council (NAMC)

  - Health Technical Advisory Panel (HeTAP)

- Participation in events organized by relevant antimony substances downstream user sectors

- Responsible for the organisation of exchanges and events hosted by i2a

- Monitor and follow-up classification and risk assessment regulatory requirements applicable to antimony substances at regional and international levels

- Responsible for keeping all Members and Directors informed on the activities of i2a and ensuring the proper progress of all i2a projects

- Guardian of i2a’s argumentation and credibility when communicating on antimony-specific regulatory concerns

Regulatory Toxicologist

Responsible for managing main i2a regulatory toxicology matters and projects, including scientific and technical activities related to the generation, harmonization and submission of data for the international regulatory processes assessing and deciding upon the hazard, exposure and risk assessment of antimony substances.

The Regulatory Toxicologist reports to the Secretary-General, to the Chair and Co-Chair of i2a, and serves the interests of i2a and all its projects.  The Regulatory Toxicologist acts as back-up for the Secretary-General of i2a on scientific and technical matters.

The main responsibilities of i2a’s Regulatory Toxicologist, supported by relevant external experts and those of i2a’s EHS Group, are:

- Monitor and follow-up classification and risk assessment regulatory requirements applicable to antimony substances at regional and international levels

- Coordinate the regular scientific literature searches and review new toxicological evidence on antimony substances, in particular as regards lung toxicity and reproductive toxicity

- Develop scientific opinions and rationale on the potential hazard and classification of antimony substances, based on the available toxicological evidence and grouping/read-across (cf. ECHA Read-Across Assessment Framework)

- Design and coordinate testing programs aimed to address toxicity and mode of action knowledge gaps about antimony substances

- Set-up and coordinate the exposure (bio-)monitoring and assessment programs, and ensure that the most recent monitoring data is included in the REACH exposure assessments and exposure scenario, considered in the derivation of Occupational Exposure Limits (OEL)/Threshold Limit Values (TLV), etc.

- Ensure the timely inclusion of new scientific evidence in updated REACH Registration Dossiers, according to the applicable ECHA Guidance documents

- Ensure the timely inclusion of new scientific evidence in updated extended Safety Data Sheets, according to the applicable ECHA Guidance documents

- Ensure the timely and scientifically robust response to the hazard, exposure or risk assessments, performed by authorities and their expert groups (e.g. ECHA, EFSA, SCOEL, NTP, ATSDR, ACGIH, etc.) as well as the related proposals and decisions

- Coordinate the preparation, submission and publication of key scientific deliverables and messages

- Represent i2a in scientific fora and groups (e.g. Human health Technical Advisory Panel (HeTAP), Eurometaux Classification and Risk Assessment Task Force, etc.), and interact with other substances consortia and associations, in particular those of other metals and those of substances antimony is commonly used with in downstream uses (e.g. bromine)

- Evaluate and advise upon the scientific services provided by external experts and consultancy research organisations and experimental institutes in the context of hazard, exposure and risk assessment

- Act as secretariat and provide technical support to i2a’s EHS Group, and to the regulatory processes applicable to antimony substances

Office Manager

Responsible for managing all i2a office and logistic needs, including communication, organisation of events, accountancy, and social secretariat/human resource items.

The Office Manager reports to the Secretary-General, to the Chair and Co-Chair of i2a, and serves the interests of i2a and all its projects.  The Office Manager acts as back-up for the Secretary-General of i2a on administrative, financial, and communication matters.

The main responsibilities of i2a’s Office Manager, supported by relevant external experts and those of i2a, are:

Administrative

- Handle day-to-day office: handling of phone calls, dealing with incoming and outcoming mail, welcoming Members and visitors, managing the stock of office supplies, dealing with different providers

- Manage/schedule calendar: plan meetings, conference calls and appointments

- Event organizer: Organise staff, technical, Assembly and ad hoc meetings and conference calls as well as social events and appointments, which includes preparing and/or circulating:

  - Invitations and provisional programmes;

  - Participants’ lists;

  - Conference call and web-conferencing details;

  - Agendas, slides, support documents, conclusions or minutes and annexes as per instruction of the meeting’s secretariat.

And organise logistics (venue, meeting rooms, meals, travel and accommodation)

- Meeting and traveling tracking: Keep meeting and travel tracking file up to date

- Co-signature: Under the guidance of the Secretary-General and/or Treasurer of i2a, act as co-signature authority on behalf of i2a (e.g.: approval of invoices, quotations, contracts, study plans, proposals, etc.)

- Membership management: Manage membership requests and agreements (including circulation of documents for signature, counter-signature by i2a, issuing of invoices, tracking of payments, issuing of contractual deliverables, and updating website and mailing lists)

- Filing and archiving: Manage hardcopy and electronic filing and archiving system

Financial and human resources

- Accounting and auditing:

  - Entry of invoices, credit notes, expense notes, credit cards, cash, bank extracts, salaries, etc. in Winbooks;

  - Weekly tracking of invoices and expense notes to be paid after approval by the Treasurer;

  - Payment of invoices via on-line banking;

  - Monthly update of expenditures tracking;

  - Prepare the annual budget, calculate annual membership fees and invoices, and presentation to Board and Assembly for approval;

  - Invoicing to Members: preparation, sending and follow-up of payments;

  - Annual update of LoA cost itemisation, number of registrants per substance and tonnage band, and resulting calculation of possible re-invoicing/reimbursement needs; and

  - Office support during annual audits of accounts.

- Human resources: Manage social secretariat items:

  - Monthly entry of officers’ services and payment of salaries;

  - Follow-up of holidays, recuperation days, sick, maternity and parental leaves, etc.;

  - Monthly ordering of lunch vouchers;

  - Ordering of eco-vouchers; and

  - Miscellaneous.

- Insurance: Follow-up and update several insurances (group, health, and civil responsibility)

Communication

- Mailing lists: Maintain and update of the office electronic database (distribution lists for Board, Assembly, and any committee, i2a website, etc.)

- Internal communication:

  - E-mails: Prepare, track, and send relevant communication material by e-mails to Members (action requests, newsletters, etc.)

- External communication:

  - i2a Website: Keep content and links updated on a yearly basis and as frequently as needed for the webpages related to news and events, publications, and SIEF communication, among others

  - Other public sources: Keep i2a-specific content and links of Eurometaux website, REACH-Metals website, etc. website updated

  - Social media: Keep i2a social media active and visible

- SIEF communication: Responsible for circulating SIEF (generic) communications to potential registrants about substance identity profile for sameness and dossier scoping discussions, identification of Lead Registrants, data-sharing, availability of Letters of Access, and other ad hoc issues

# Annex 4 – i2a Expanded networking organizational structure

Quantitative structure–activity relationship between substances