i2a Communication Plan 2019-2020

Brussels, 20 February 2019

Version 1.0

NOTE TO THE READER:

This draft document (version 1.0) has been updated by the i2a Secretariat following the 24 January 2019 Communication Group meeting and the revision by an external Communication expert in February 2019.  This version can be implemented in 2019 (and 2020).

Contents

1.	BACKGROUND	3

1.1.	Vision, Mission, Mandate and Strategic objectives of i2a	3

1.2.	General communication objective of i2a	3

1.3.	Situation analysis (regarding the general communication objective)	4

2.	SPECIFIC OBJECTIVES OF THE COMMUNICATION PLAN	5

2.1.	Who should i2a communicate with?	5

2.2.	What information should i2a communicate?	6

2.3.	How should i2a communicate its information?	7

3.	2019-2020 i2a COMMUNICATION DELIVERABLES	9

3.1	Specific tasks to develop in order to implement Communication Calendar	9

3.2	2019 Communication Calendar	10

3.3	Short description of 2019-2020 deliverables	11

4.	EVALUATION OF THE COMMUNICATION PLAN AND ITS DELIVERABLES	13

# BACKGROUND

# Vision, Mission, Mandate and Strategic objectives of i2a

The vision, mission, and strategic objectives outlined in i2a’s Product Stewardship Strategy are provided below:

i2a Vision: a sustainable and responsible Sb industry, where Sb substances continue to be the material of choice for many technology-enabling applications.

i2a Mission/Mandate: To inspire product stewardship throughout the Sb value chain to ensure safe use and responsible management of Sb substances.

i2a Strategic objectives:

- Address knowledge gaps weakening the safe use and positive image of Sb substances

- Ensure that the most up to date evidence is used in any regulatory scrutiny of Sb substances

- Determine the most relevant, proportionate, and efficient risk management measures applicable for each use of Sb substances

- Support the Sb industry in implementing responsible product stewardship practices

# General communication objective of i2a

In order to build the communication plan, a specific communication objective is defined for each one of the strategic objectives outlined above:

Table 1. Communication objectives related to i2a’s strategic objectives.

| Strategic objective | Specific communication objective | General communication objective |
| --- | --- | --- |
| Address knowledge gaps weakening the safe use and positive image of Sb substances | Spread complete and clear information about the frequency and variety of safe usage and positive contribution/societal value of Sb substances. Relate this message to Sb’s longstanding heritage. | Increase the visibility and credibility of Sb substances and of i2a |
| Ensure that the most up to date evidence is used in any regulatory scrutiny of Sb substances | Publish the latest and most robust evidence about hazard, exposure and risk, but also socio-economic value of Sb substances |  |
| Determine the most relevant, proportionate, and efficient risk management measures applicable for each use of Sb substances |  |  |
| Support the Sb industry in implementing responsible product stewardship practices | Develop tailored communication materials facilitating the implementation of best practice for traders, producers, and users of Sb substances |  |
|  | Enlarge the geographical and market/substance coverage of i2a |  |
|  | Promote i2a as THE unique reference for all the antimony EHS |  |

# Situation analysis (regarding the general communication objective)

Increasing the visibility and credibility of Sb substances needs to take account of the existing situation, starting with the general perception and underlying ‘arguments’ put forward by supportive and skeptical stakeholders of the Sb value chain, respectively:

Table 2. Perception of Sb by supportive and skeptical stakeholders (taken from i2a Strategy)

| Why Sb? | Why not Sb? |
| --- | --- |
| Not scarce, sufficient reserves in the world compared to demand | High dependence on Chinese providers and other controversial territories (responsible sourcing questioned) |
| Extracted as a by-product of gold mining, maximizes efficiency of extraction of scarce material | Also associated to environmental releases of Pb and As which co-exist with Sb in some mines |
| Good price, good value for money | Volatile pricing |
| Multi-function, versatile (can be used in many physical and chemical forms), relatively small quantities needed | - Dispersed presence in many articles - Contributes to continued used of Brominated flame retardants, Pb, PVC, PET, and other environmentally non-friendly materials |
| Despite being a (heavy) metalloid, it is relatively inert | - Associated to lung cancer, increase in spontaneous miscarriages, dermal irritation and other organ-specific toxicities, as well as autism - Undocumented workplace and consumer exposure |
| Makes applications more resource efficient (synergist: less brominated flame retardant needed to reach same performance, better throughput and quality of PET catalysis) | Contributes to applications which are not strictly necessary (e.g. flame retardancy used beyond strict industrial and professional needs) |
| Recyclable, contributes to Circular Economy goals | Recycling beyond metallic applications not sufficiently explored/ensured |
| Not controversial, relatively low on authorities’ radar screen | Could become more controversial if above issues are not addressed, regulatory pressure is generally increasing worldwide |

The general perception on Sb substances will be influenced by the available scientific evidence and the regulatory scrutiny resulting from the assessment of such evidence, in a number of contexts:

- Some evidence of cancer in rats and clear evidence of cancer in mice in the NTP report (2-year inhalation carcinogenicity studies on antimony trioxide) = possible reclassification as Carc. Cat 1B (presumed carcinogen) instead of Carc. Cat 2 (suspected carcinogen).

- Additional classification as STOT RE 2 (Specific Target Organ Toxicity (STOT) upon Repeated Exposure (RE))

- Possible reproductive toxicity and endocrine disruptor questioned by the authorities = need of more testing and/or extra classification

For i2a to be the porte-parole of an enhanced visibility and credibility of Sb substances, the visibility of i2a and the credibility of i2a’s expertise in the above regulatory arena must be addressed hand in hand with the visibility and credibility of Sb substances.  Where i2a will be visible and credible, so will be Sb substances, and vice-versa.  So far however:

- i2a is not yet THE unique reference for all the antimony related questions

- All the Sb value chain is not under the umbrella of i2a

- i2a today is not operating on a truly international level, but is more Eurocentric

# SPECIFIC OBJECTIVES OF THE COMMUNICATION PLAN

i2a’s Communication Plan formally defines who among the stakeholders of the Sb Value Chain should be given specific information, what information each one should receive, and how the information should be delivered (when and what communication channels will be used).

The Communication Plan is written in such a manner that it can guide the communication team in the preparation of its deliverables, ensure that consistent and accurate information is conveyed in the right format and at the right time, and that the relative success of the Plan and its deliverables can be assessed and measured.

More specifically, it provides a clear roadmap for consistently communicating with i2a stakeholders, so they feel invested in the process and are well informed about goals, or a specific initiative, and can take action and help achieve those goals.

# Who should i2a communicate with?

The stakeholders i2a should communicate with is composed of two types of audiences: those with whom i2a will establish a (pro-)active communication, and those with whom it will establish a more reactive or passive communication:

|  | (Pro-)Active | Reactive/Passive |
| --- | --- | --- |
| Internal | - i2a Full Members (+) - i2a Associate Members (+) |  |
| External | - Regulators & Authorities (-) - Value Chain (excluding existing Members but including potential Members, also those organized via associations) (+/-) - Advocacy partners (+) - Media partners (+/-) | - Public (+/-) - NGOs (+/-) |

Table 3. Types of i2a audiences and their related communication approaches

(+) Generally have a more positive perception of Sb

(-) Generally have a more negative perception of Sb

The key target audiences are regulators and authorities, and the value chain.

As regards NGOs and the public, i2a’s communication will be limited to reacting if and when there is any negative front-page news, responding to myths/rumors and misunderstandings around Sb.  Reactive communication will be actioned against major incorrect statements / opinions / proposals and decisions, on a case-by-case basis.  Beyond this, these audiences may passively receive i2a’s communication aimed at its key target audiences.

# What information should i2a communicate?

The communication objectives per key target audience are:

| Specific communication objective | Regulators and authorities | Value chain |
| --- | --- | --- |
| Spread complete and clear information about the frequency and variety of safe usage and positive contribution/societal value of Sb substances. Relate this message to Sb’s longstanding heritage. | X | X |
| Publish the latest and most robust evidence about hazard, exposure and risk, but also socio-economic value of Sb substances | X |  |
| Develop tailored communication materials facilitating the implementation of best practice for traders, producers, and users of Sb substances |  | X |
| Enlarge the geographical and market/substance coverage of i2a |  | X |
| Promote i2a as THE unique reference for all the antimony EHS | X | X |

Key general messages that should be contained in any i2a communication (and possible variations or use-/audience-specific messages) are:

Table 4. Key general and specific messages to be delivered through i2a communication

| Topic | Key message | Variations and use-/audience-specific messages |
| --- | --- | --- |
| About Sb | Sb is safe | Sb’s hazards do not imply risk, there is no risk of Sb without exposure to Sb, adverse effects is prevented through controlled exposure, etc. |
|  | Sb contributes to safety | Sb makes your life safer, Sb makes your family’s life safer, Sb: Keeping you and your family safe, Sb: helping us all lead safer lives, Sb for safer living, Sb: keeping all of us safe, etc. |
|  | Sb is efficient | Sb is cost- and resource-efficient, using an Sb oxide decreases the amount of expense Brominated flame retardant by a factor of 3, a gram of Sb compound can produce X tons of PET resin, etc. |
|  | Sb is circular | Sb containing end-of-life and wastes can be sorted out and recycled or incinerated with energy and Sb recovery opportunities, etc. |
|  | Sb has history | Sb has a positive history of significant and safe societal benefits. |
|  | … |  |
| About i2a | i2a is your regulatory expert | reference toxicology dataset, hazard assessment and classification, exposure and risk assessment, workplace limits, product limits, etc. |
|  | i2a is the home of the Sb Value Chain | No data = harsh regulations = no market, the Sb Value Chain is as weak as its weakest link, producers and traders alone will not carry enough socio-economic weight for advocacy, etc. |
|  | … |  |

In addition to the above key (and specific) messages, i2a should communicate about new, or updated/revised information, and in each case, what i2a’s position is, and what it entails for each actor of the Value Chain:

Table 5. Information to be communicated about Sb and i2a to Sb stakeholders

| Topic | Information to be communicated |
| --- | --- |
| About Sb | - Toxicology, hazard levels, classification evidence related to Sb substances - Exposure evidence, Threshold Limit Values and Occupational Exposure Limits related to Sb substances - Workplace and environmental legislation (including waste and circularity) applicable to Sb substances - Product legislation applicable to Sb substances - Research for alternatives/substitutes to replace Sb substances - Innovative uses of Sb substances - Socio-economic costs and benefits related to Sb substances - … |
| About i2a | - i2a’s leadership in latest environmental and health information for the production and use of Sb and compliance with EU-REACH and similar legislation - i2a’s position on each one of the above new or updated/revised information - Status of i2a membership (Sb substances covered, geographical regions covered, uses/markets covered, etc.) - i2a’s events and communication materials - … |

# How should i2a communicate its information?

The available communication tools and their related frequency of use are:

Table 6. i2a Communication types, tools and frequency

| Communication type | Communication tool | (Minimum) Frequency |
| --- | --- | --- |
| Non-media | - i2a Board meetings | 2/year |
|  | - i2a Board calls | 2/year |
|  | - i2a General Assembly meetings | 2/year |
|  | - i2a General Assembly calls | 2/year |
|  | - i2a Groups (and Task Forces) meetings | 1/year |
|  | - i2a Groups (and Task Forces) calls | 10/year |
|  | - i2a Technical workshops | 1/year |
|  | - i2a Sb Days | 1/year |
|  | - External events | 2/year (one in EU and one abroad) |
|  | - Other associations and companies’ meetings and calls | 4/year |
| Media | - Mails | When action is required |
|  | - Newsletters Internal | 4/year (trimestral version) |
|  | - Press Releases | As necessary (minimum 2/year) |
|  | - Factsheets | As necessary (minimum 2/year) |
|  | - Scientific publications | As necessary (minimum 1/2-year) |
|  | - General presentation of i2a | 4/year (trimestral update) |
|  | - Annual report | 1/year |
|  | - Website (Members-only) | 12/year (monthly update) |
|  | - Website (Public) | 12/year (monthly update) |
|  | - Social Media | 24/year (two posts per month) |
|  | - Posters, booklet, goodies, etc. | 1/year |
|  | - Other associations’ and companies’ communication materials | 4/year |

The communication tools per type of stakeholder or audience of i2a are:

| Stakeholders | (Pro-)Active | Reactive/Passive |
| --- | --- | --- |
| Internal | - i2a Full Members (All communication tools) - i2a Associate Members (All communication tools) |  |
| External | - Regulators & Authorities (7, 8, 9, 14, 15, 19, 20) - Value Chain (5, 6, 7, 8, 9, 10, 13, 14, 16, 19, 20, 21, 22) - Advocacy partners (13,14,15,19, 20, 21) - Media partners (8, 9, 13, 15, 19, 20) | - Public (19, 20, 21) - NGOs (19, 20, 21) |

Table 7. Communication tools per audience (combining Tables 3 and 6)

Before information is communicated to wide audiences, it will be produced and reviewed through the following steps, in order to validate its content:

Figure 1. i2a’s communication contents preparation and validation steps

Where time does not permit full consultation, release will be actioned after the 3rd step.

# 2019-2020 i2a COMMUNICATION DELIVERABLES

The following deliverables have been defined for 2019 (as kick-off year of the i2a formal Communication Plan), and will be repeated / updated for 2020.

# Specific tasks to develop in order to implement Communication Calendar

The following tasks have been identified for implementation in 2019:

Table 9. Specific tasks related to each communication tool for 2019

| Communication tool | Specific tasks (for 2019) |
| --- | --- |
| General | - For each communication tool, define an agreed content and format check-list - Update i2a mailing lists for each Group, TF, and external outreach - Segment i2a mailing list per region, DU, etc. to enable a more focused communication - Put in place a more efficient e-mail automation service (e.g. mailchimp, prnewswire.com, or similar) - General: - Work with communication/infographics expert to brand any public/external communication material produced - Identify resource needs for above tasks |
| Members-only meetings or conference calls | - Agenda and background documents sent at least 1 week before - Conclusions sent latest 2 weeks after |
| Open meetings or conference calls | - Date announced at least 6 months before - Dedicated webpage set-up at least 3 months before for technical workshops, and 6 months before for Sb Days - Agenda made available at least 3 months before - Takeaways made available latest 2 weeks after - i2a Presentations made at at least 4 non-i2a events, targeting DU awareness-raising in main DU sectors (Flame retardants, PET, Pb alloys and batteries) |
| Members only documents or emails | - Newsletters circulated once per trimester (4 per year) - Newsletters do not exceed 2 pages - Annual Report circulated in January after the closed year - Annual Report does not exceed 4 pages - i2a Basic presentation updated once per trimester - i2a Basic presentation used in at least 4 events where i2a Members are presenting |
| External documents or emails | - At least 3-4 Press media in which to publish i2a articles identified (e.g. (e.g. ChemWatch, Metal Bulletin, Compounding, ComPETence, etc.) - At least 4 Press releases per year, and their respective factsheet with more detailed information - Factsheets updated at least once per trimester - Newsletter circulated once per semester (2 per year) - At least 2 articles in selected press |
| Media Internal | - Agreed menu of contents (minimum: by-laws and governance rules, job descriptions of i2a staff, i2a Product Stewardship and related plans, conclusions and annexes of meetings and calls) - Members-only updated once per month |
| Media External | - Agreed frame and information to be posted on website - All website pages completed - Website updated once per month - LinkedIn/Twitter accounts established - All i2a Members following i2a LinkedIn/Twitter account - At least one i2a LinkedIn/Twitter post per week (related to e.g.: i2a, Member activities, the 10 compounds, Sb Industry and uses, Regulation, Achievements, positive case examples, etc.), including animated and video posts and links to the i2a website for more information - Build ‘buzz’ before, during and after events, to leverage interest and investment in these - At least 2 shares per post |
| Printed material | - Reuse existing posters as much as possible - At least one dedicated poster per open meeting - At least one goodie per open meeting |

# 2019 Communication Calendar

For 2019, the following Communication calendar is proposed:

Table 8. i2a 2019 Communication Calendar

| Communication deliverable | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Board conf call |  | 19 |  | 25 |  |  |  |  | 11 |  |  |  |
| Board meeting |  |  |  |  | 15 |  |  |  |  |  |  |  |
| GA conf call |  | 28 |  |  |  |  |  |  | 30 |  |  |  |
| GA meeting |  |  |  |  | 16 |  |  |  | 30 |  |  |  |
| Membership TF conf call | x |  |  |  |  |  |  |  | x |  |  |  |
| EHS Group conf call | x | x | x | x | x | x |  |  | x | x |  | x |
| Communication Group conf call | x |  | x |  | x |  |  |  | x |  | x |  |
| Tox TF conf call (upon necessity) |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring TF conf call (upon necessity) |  |  |  |  |  |  |  |  |  |  |  |  |
| RoHS TF conf call (upon necessity) |  |  |  |  |  |  |  |  |  |  |  |  |
| Technical workshop |  | 21 |  |  |  |  |  |  |  |  |  |  |
| Sb Day |  |  |  |  |  |  |  |  |  | 15 |  |  |
| (non-i2a) External event |  |  | x | x |  |  |  |  |  |  | x | x |
| Newsletters / Internal News |  |  | x |  |  | x |  |  | x |  |  | x |
| Factsheets (linked to Press Releases) |  |  |  |  |  |  |  |  |  |  |  |  |
| Website (members only) | update | update | update | update | update | update | update | update | update | update | update | update |
| Annual report |  |  |  |  | x |  |  |  |  |  |  |  |
| Sb Positives | x | x | x | x | x | x | x | x | x | x | x | x |
| Website Public | update | update | update | update | update | update | update | update | update | update | update | update |
| Press releases (upon necessity) |  |  |  |  |  |  |  |  |  |  |  |  |
| Other associations' and companies' releases (tailored) |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Media | x | x | x | x | x | x | x | x | x | x | x | x |
| i2a Booklet / Basic presentation |  |  |  |  |  |  |  |  |  |  |  |  |
| Roll-ups / posters / goodies |  |  |  |  |  |  |  |  |  | x |  |  |

With the following color-code:

Members only meetings or conference calls

Open meetings or conference calls

Members only documents or emails

External documents or emails

Social media

Printed material public

# Short description of 2019-2020 deliverables

| Communication deliverable | Short description |
| --- | --- |
| Board conf calls and meetings | Regular exchanges to update and decide upon strategic matters of relevance to i2a and Sb related EHS regulations (upon recommendation from EHS and Communication Groups) |
| GA conf calls and meetings | Regular exchanges to update and decide upon strategic matters of relevance to i2a and Sb related EHS regulations (upon recommendation from Board) |
| Membership TF conf call | Ad hoc exchanges to address membership-related questions such as cost-sharing, outreach, etc. |
| EHS Group conf call | Regular exchanges to update and recommend approach for matters related to Sb related EHS regulations (upon recommendation from the Tox TF, Monitoring TF and/or RoHS TF) |
| Communication Group conf call | Regular exchanges to update and recommend approach for matters related to the internal and external communication of i2a |
| Tox TF conf call (upon necessity) | Regular exchanges to update and recommend approach for matters related to the toxicological testing of Sb substances for the purpose of EHS compliance |
| Monitoring TF conf call (upon necessity) | Regular exchanges to update and recommend approach for matters related to the monitoring of Sb generated during production and use in workplaces |
| RoHS TF conf call (upon necessity) | Regular exchanges to update and recommend approach for matters related to the possible restriction of use of Sb in electric and electronic articles |
| Technical workshop | Annual workshop to inform and train producers and users of Sb about a specific best practice, such as proper monitoring of workplace exposure to Sb Typically one day, in Brussels Free of charge for Members, participation fee for non-Members Support from technical experts |
| Sb Day | Annual public event to update all audiences about regulatory horizon of Sb and use-specific aspects Good opportunity (during registration for event) to collect feed-back from audiences on e.g. where Sb information is most often searched from Typically one day, in Brussels Free of charge for Members, participation fee for non-Members Presentations from external experts |
| (non-i2a) External event | Participation from i2a representative in non-i2a event Can be a company, an association (e.g. EuMBC), or a network/sector (e.g. AMI) event Typically in EU, with one event per year taking place outside the EU (North America or Asia) |
| Newsletters / Internal News | Document updating i2a Members about high-level aspects of i2a and Sb related EHS regulations once per trimester Between 5 and 8 articles per newsletter, maximum 2 pages Each article can be posted on social media as a teaser |
| Factsheets (linked to Press Releases) | Document compiling high level ‘all you need to know’ information on a given substances or EHS regulatory process relevant for Sb Will typically be an internal document, announced in a press release on the topic of interest |
| Website (members only) | Library of i2a or Sb related EHS documents for i2a Members only |
| Annual report | Annual overview of i2a’s activities, achievements, budgets |
| Sb Positives | Stories populated by i2a Members and communication experts to spread good news about Sb (and balance negative news related to regulations) One positive news per month to start with: Did you know? or What would life be without? type of contents About: Sb’s history, use in cosmetics, use in cables, use in cars (decreased weight + increased safety), use in medicine, heritage, etc. |
| Website Public | i2a public website Should appear first whenever someone searches ‘antimony’ on a browser Should provide sufficient high-level information to motivate the reader’s interest, without giving away too much details Should profile i2a as the leader in EHS compliance data for Sb |
| Press releases (upon necessity) | Public announcements about i2a or Sb to be shared publicly More detailed information on the topic would typically be compiled in a factsheet, normally reserved for i2a Members only |
| Other associations and companies' releases (tailored) | Releases from associations of companies producing or using (articles requiring) Sb I2a Secretariat can ask that Sb articles are spread through these releases |
| Social Media | i2a’s LinkedIn and Twitter accounts through which specific posts are shared Replications from Newsletter’s articles + i2a-specific contents should be posted as teasers, to attract visitors to i2a website Works efficiently only if i2a posts are shared by the broader Sb network |
| i2a Booklet / Basic presentation | i2a’s presentation to be used by any Member having to present i2a externally Can be a power point presentation or another type of material |
| Roll-ups / posters / goodies | Communication material to increase the branding and visibility of i2a and Sb Typically produced for Sb technical workshops and events |

# EVALUATION OF THE COMMUNICATION PLAN AND ITS DELIVERABLES

The implementation of the communication plan will be evaluated by the Communication Group every 6 months, and the impact achieved through its deliverables every year (and reported in the Annual report after approval by the Board).

The implementation and impacts will be evaluated against the specific tasks identified in Table 9 above.

Those tasks should ultimately enable to produce the following impact:

- Improve the periodicity and visual consistency of all online and offline communication materials in order that messaging from i2a is easily recognizable as such

- Reposition i2a as a voice of authority related to EHS regulations and product stewardship matters

- Enable important conversations and engagement with stakeholders about key communication contents (i2a actions and evidence needs)

- Increase the engagement of the Sb value chain in i2a’s product stewardship initiative, either via increased membership or partnerships

- Raise awareness about the most recent, high quality, results of the research programs conducted by i2a related to the safe use and positive image of Sb substances

- Raise the positive profile of Sb substances and tackle/reduce the negative profile of Sb substances

The implementation of the Communication Plan should, as far as possible, be evaluated against the specific tasks and the desired impacts.