## Detailed Progress
2019-02-18
|  | Admin tracking |  |  |  |  | Progress tracking |  |  | Expenditure tracking
Main regulatory driver | Work item | Scientific aim | Regulatory aim | External Partner | i2a Group/Secretariat | Main Reg or Sc authority | Done so far/Pending | Completion status | Comment | Full project quote | Budgeted for 2019 | Contracted | Invoiced/Paid | Left to pay
REACH Substance Evaluation | REPROTOX: Bioelution gastric | Compare and rank Sb substances according to bioavailability in artificial gastric juice | 1) Inform read-across for oral endpoints 2) Identify relevant test items for reprotox testing | ECTX VITO | Tox TF/M. Huppert | BAuA, ECHA, EU-COM | - Identify and supply substances - Agree and prepare media composition - Validate quantification and speciation of Sb in media - Receive and review draft Study Plans - Complete of samples' information - Agree on final Study Plans - Run tests - Check draft reports (including difference of results with and without proteins) - Finalize reports - 'Rank' Sb substances - Identify most representative Sb sample for reprotox testing | 40% | Study plans will be finalized by end Jan | 109644 | 109644 | 109644 | 0 | 109644
REACH Substance Evaluation Classification | REPROTOX: Tailored OECD 422 test | Understand maternal toxicity and delayed ossification caused (?) by Sb in other studies | 1) Postpone and inform/reduce scope/cost of mandatory EOGRTS test 2) Confirm no reproductive toxicity classification | ENVIGO L. Aveyard | Tox TF/M. Huppert | BAuA, ECHA, EU-COM, US-TSCA | - Assess all evidence and summarize possible next steps in opinion paper - Select external expert: Dr Lindsay Aveyard - Agree on tailored OECD 422 test as preferred next step - Select laboratory: ENVIGO - Agree on draft protocol with Tox TF - Share draft protocol with BAuA - Check BAuA's response: recommendation to wait for SEv draft decision before starting test - Check BAuA's SEv reproductive toxicity testing decision - Adjust original testing protocol - Identify most representative Sb substance for testing and request it - Finalize protocol - Start test - Check draft report - Finalize report - Update REACH Dossier with new information and next steps - Consider preparing scientific publication about findings | 25% | Draft SEv decision will likely contain a request for an OECD 422 | 396688.656 | 198344.328 | 198344.328 |  | 198344.328
REACH Substance Evaluation Classification | LUNG TOX: In vitro lung test (first phase) | Compare and rank inhable Sb substances around lung toxicity | 1) Inform read-across/grouping for carcinogenicity classification 2) Identify relevant test items for lung toxicity testing | IOM Craig Boreiko | Tox TF/M. Huppert | BAuA, ECHA, EU-COM, US-NTP, US-TSCA | - Assess all evidence and summarize possible next steps in opinion paper - Agree on tailored in vitro lung test as preferred next step - Select partner: IOM - Receive and discuss draft protocol with IOM - Discuss/approve updated draft protocol to Tox TF - Send final protocol to BAuA - Adjust protocol as per BAuA's comments (or similar/related testing requirements in SEv draft decision) - Finalize protocol and request samples - Start test - Check draft report and exchange about following tiers - Finalize report - Update REACH Dossier with new information and next steps - Consider preparing scientific publication about findings | 20% | In vivo test will likely be needed for at least one Sb 5+ substance | 108588.48 | 108588.48 |  |  | 0
REACH Substance Evaluation Classification RMOA | LUNG TOX: Genotoxicity research | Predict the (absence of) direct genotoxicity properties among Sb substances + inform MoA behind carcinogenicity | 1) Inform read-across for genotoxicity endpoints 2) Inform (non-)threshold carcinogenicity MoA (safe use possible below exposure level) 3) Inform (non-)mutagenicity classification | Craig Boreiko | M.Huppert | BAuA, ECHA, EU-COM, US-NTP, US-TSCA | - Assess all evidence and identify possible next steps in opinion paper - Prepare draft research plans - Discuss draft research plans with Tox TF - Request for quote for agreed research avenues | 15% | 3 tests ar considered:in vitro MN induction, commet assay reslts on tissue block from NTP study, oncogen activation studies | 130000 | 130000 |  |  | 0
All | LUNG TOX: Scientific publication on Sb results in ToxTracker | Make available to scientific community the results of ToxTracker assay applied on all Sb substances | Strenghten argumentation and reasonning that Sb substances overall are not direct genotoxicants | Rita Cortvindt Craig Boreiko | Tox TF/M. Huppert | BAuA, ECHA, EU-COM, ACGIH, US-NTP, US-TSCA, etc. | - Agree on content of publication and quote - Finalize Tox tracker studies - Prepare first draft article on ToxTracker - Review drafts - Agree on final publications - Identify scientific journals - Follow-up publication - Share/Signal publication to relevant readers | 40% | First draft expected end Jan | 15750 | 15750 | 10500 | 5000 | 5500
All | LUNG TOX: Scientific publication on Sb genotoxicity | Make available to scientific community the right information on antimony genotoxicity | Strenghten argumentation and reasonning that Sb is not a direct genotoxicant and that it is a threshold carcinogen (safe use below a given exposure level is possible) | Craig Boreiko Toby Rossman | Tox TF/M. Huppert | BAuA, ECHA, EU-COM, ACGIH, US-NTP, US-TSCA, etc. | - Agree on content of publication and quote - Identify co-author - Prepare draft article on genotoxicity of Sb - Review drafts - Agree on final publications - Identify scientific journals - Follow-up publication - Share/Signal publication to relevant readers | 40% | Additional work in the meantime have delayed the delivery of drafts. | 41853 | 41853 | 41853 | 4400 | 37453
REACH Substance Evaluation Classification | LUNG TOX: Poorly Soluble Low Toxicity (PSLT) substances debate | Develop robust understanding on the actual hazard of, exposure to and risk of PSLTs | 1) Obtain recognition that carcinogenicity is not a chemical effect but a(n indirect) result of a physical effect of excessive exposure to particles 2) Derive safe levels (workplace exposure, derived minimal/no effect levels or D(M/N)ELs, and/or specific concentration limits (SCLs) for PSLTs | Paul Borm Kevin Driscoll HeTAP (Health Technical Advisory Panel) Craig Boreiko | M.Huppert |  | - Clarify aim and benefits of workshop, and i2a's sponsorship - Confirm participation in 1-2 April Workshop in Edinburgh - Confirm Agenda, timings, and participants with organizers - Identify BAuA representative for workshop - Organize i2a's experts participation (in meeting: Craig Boreiko, via call: Marjorie Huppert, from IOM: Matthew?) - Craig to produce notes from the workshop + comparison TiO2/ATO and share with i2a Secretariat - i2a Secretariat to share final notes and comparison with i2a Members - Discuss about follow-up and next steps with organizers and other sponsors | 25% | External to i2a | 14700 | 0 | 14700 | 9881.1304 | 4818.8696
REACH Substance Evaluation RMOA TLV/OEL setting | LUNG TOX: Workplace exposure data collection + pilot bio-monitoring | Document latest exposure levels in producing and using sites | 1) Demonstrate safe production and use with hard data (minimum uncertainty) 2) Use in TLV/OEL revisions processes 3) (Develop approach to or) Demonstrate compliance with stricter TLV/OELs | IOM HSL (for bio-monitoring) | Monitoring TF/C. Braibant | BAuA, ECHA, EU-COM, ACGIH, US-NTP, US-TSCA | - Develop and validate sampling and analytical methods - Identify partner: IOM - Finalize Monitoring Campaign presentation material - Invite i2a Members and non-Members to join - Secure participation of at least 10 companies - Check that participating companies meet coverage needed (substance, geographical, use) - Finalize Monitoring Guidance and data collection spreadsheet - Organize and hold kick-off workshop in Feb 2019 - Identify and secure additional participants - Finalize MoU for participating companies - Identify companies willing to work with IOM for monitoring (to include PSD and urine) - Launch first year of monitoring campaign - Collect initial findings for presentation at Sb Day - Refine and launch second year of monitoring - Inform BAuA/ECHA + ACGIH | 30% | Open to i2a Members and non-Members | 159884.075 | 59574.6375 | 159884.075 |  | 159884.075
REACH Substance Evaluation RMOA | LUNG TOX: Exposure data collection in indoor shooting ranges | Document Sb exposure levels in shooting ranges using Sb-containing bullets | Demonstrate safe use of Sb in bullets | Belgian Federal Police | Monitoring TF/C. Braibant | BAuA, ECHA, EU-COM | - Meet with AFEMS and other EU associations related to ammunitions - Meet with Belgian Federal Police to check interest in monitoring - Develop initial monitoring protocol and costing and share with Belgian Federal Police for comment - Discuss with Monitoring TF/Board (regarding budget implications vs importance of retaining use in REACH Dossiers) | 0% | Specific request/concern from BAuA | 68552.4 | 0 |  |  | 0
REACH Substance Evaluation RMOA | ADVOCACY: REACH Substance Evaluation | Identify knowledge gaps and generate evidence to tackle these in a scientifically robust manner | Replace uncertainty by hard evidence to avoid worst-case conservative decision-making re additional information requirements, classification, further risk management measures needed | Eurometaux (Accredited Stakeholder to ECHA) | EHS Group+Board/C. Braibant | BAuA, ECHA, EU-COM | - Meet with BAuA - Update all i2a REACH Dossiers - Share i2a research and workplace monitoring plans with BAuA - Monitor release of draft SEv decision - Provide comments on draft SEv decision - Monitor Member State comments and BAuA's response to comments - Adjust research and monitoring plans according to draft decision - Launch (adjusted) research and monitoring plans - Update Dossiers with new evidence/inform BAuA of progress - Monitor release of final SEv decision - Adjust research and monitoring plans according to final decision - Update REACH Dossiers/inform BAuA on progress | 15% | Draft SEv is expected by end Mar/early Apr | 0
Classification | ADVOCACY: Classification | Identify knowledge gaps and generate evidence to tackle these in a scientifically robust manner | Replace uncertainty by hard evidence to avoid worst-case conservative decision-making re classification | Eurometaux (Accredited Stakeholder to ECHA) | EHS Group+Board/C. Braibant | BAuA, ECHA, EU-COM | - Monitor CLH proposal release | 0% | Classification proposal will come after SEv decision | 0
RMOA | ADVOCACY: RMOA | Identify remaining risks potentially associated with the use of Sb and most appropriate risk management measure to tackle such risk | Anticipate an increase of regulatory requirements and limitations imposed on the use of Sb, and inform on the most proportionate regulatory approach | Eurometaux (Accredited Stakeholder to ECHA) RMOA expert SEA expert (e.g. Roskill) | EHS Group+Board/C. Braibant | BAuA, ECHA, EU-COM | - High-level analysis of impact of reclassification done - Tool to quantify societal value of Sb under development - Collection of exposure data planned - Finalize SEA tool - Monitor follow-up risk management measures recommended in SEv decision | 0% | RMOA not formally part of i2a work, but work items alrady contributing to RMOA evidence review and generation | 0
RoHS | ADVOCACY: RoHS | Identify knowledge gaps around the use of Sb in electric and electronic equipment and generate evidence to tackle these in a scientifically robust manner | 1) Contribute to development of robust RoHS restriction methodology 2) Prevent addition of Sb to Annex II of the RoHS Directive | RoHS Cross-Industry Group (with Cefic & Eurometaux) | RoHS TF+Board/C. Braibant | EU-COM | - RoHS TF created - Response to Sb-specific questionnaire submitted - Response to draft RoHS restriction methodology submitted - Organize/Participate in meeting with the EU Commission (and Eurometaux and Cefic) - Monitor release of Initial Dossier on ATO - Monitor release of second draft methodology - Participate in industry meeting with Commission | 40% | Pack 15 project supposed to deliver final output in July 2019… followed by formal restriction proposals by EU-COM | 0
Note on K7: Caroline: Place-holder only, while more specific protocols become available
Note on L10: Caroline: Not budgeted per se, but part of risk assessment and classification updates under REACH

## Progress
2019-02-18 | Internal assessment (5%) | Identification and contact with partner(s) (5%) | Agreement on purpose (5%) | Receipt of quotes/study plan (5%) | Circulation to/approval by relevant TF, Group and BoD (5%) | Revision of study plan/quotes (5%) | Signature of contract, start of the project (5%) | Request/Receipt of test samples (5%) | Release and review of results/first draft (30%) | Reception/Review of final draft report by i2a (20%) | Conclusion of project, definition of next steps (10%) | Completed
EHS strategy
REPROTOX: Bioelution gastric | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |  |  |  | 40%
REPROTOX: Tailored OECD 422 test | 5% | 5% | 5% | 5% | 5% | [6 empty] | 25% | completed
LUNG TOX: In vitro lung test (first phase) | 5% | 5% | 5% | 5% | [7 empty] | 20%
LUNG TOX: Genotoxicity research | 5% | 5% | 5% | [8 empty] | 15%
LUNG TOX: Scientific publication on Sb results in ToxTracker | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |  |  |  | 40%
LUNG TOX: Scientific publication on Sb genotoxicity | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |  |  |  | 40%
LUNG TOX: Poorly Soluble Low Toxicity (PSLT) substances debate | 5% | 5% | 5% | 5% | 5% | [6 empty] | 25%
LUNG TOX: Workplace exposure data collection + pilot bio-monitoring | 5% | 5% | 5% | 5% | 5% | 5% | [5 empty] | 30%
LUNG TOX: Exposure data collection in indoor shooting ranges | 5% | 5% | 5%
ADVOCACY: REACH Substance Evaluation | 5% | 5% | 5% | [8 empty] | 15%
ADVOCACY: Classification | 5%
ADVOCACY: RMOA
ADVOCACY: RoHS | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |  |  |  | 40%

## Timeline
2019-02-18 | 2018 |  |  |  | 2019 | [11 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
| Q1 | Q2 | Q3 | Q4 | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Work tasks
REPROTOX: Bioelution gastric | bar: Jan to May
REPROTOX: Tailored OECD 422 test |  |  |  |  | Jan: Paused
LUNG TOX: In vitro lung test (first phase)
LUNG TOX: Genotoxicity research
LUNG TOX: Scientific publication on Sb results in ToxTracker
LUNG TOX: Scientific publication on Sb genotoxicity
LUNG TOX: Poorly Soluble Low Toxicity (PSLT) substances debate
LUNG TOX: Workplace exposure data collection + pilot bio-monitoring |  |  | BAuA OEL |  | Feb: ACGIH Sb news
LUNG TOX: Exposure data collection in indoor shooting ranges
ADVOCACY: REACH Substance Evaluation |  |  |  |  | Apr: SEv Draft Decision; May: 30 days to comment; Jun: 6-12 mo for Baua to amend the draft decision and to report (amended) decision + 30 d for ECHA and MSCA to propose amendments + 30 days for registrants to comment proposed amendments |  |  | SEv Final Decision?
ADVOCACY: Classification
ADVOCACY: RMOA
ADVOCACY: RoHS | COM Meeting | Stakeholder consultation |  | Stakeholder consultation
Calendar of meetings and calls
i2a BoD |  |  |  |  | Feb: 19: Call; Apr: 25: Call; May: 15: Meeting; Sep: 30: Meeting; Dec: Call
i2a GA |  |  |  |  | Feb: 28: Call; May: 16: Meeting; Sep: 30: Meeting
i2a Com Group |  |  |  |  | Jan: 24: Meeting
i2a EHS |  |  |  |  | Feb: 14: Call; Apr: Mail communication; Jun: Meeting in Brussels; Aug: Call; Oct: Call; Dec: Call
i2a Toxicologists TF
i2a Monitoring TF
i2a RoHS TF
i2a Public Events |  |  |  |  | Feb: 21: Wokplace monitoring workshop; Oct: 2: Sb Day
External events |  |  |  |  | Mar: PET Value Chain; Apr: - PSLT Workshop - AMI Fire resistance; Jun: AsianMetal?