General Assembly meetings

ACTIONS

| Meeting date | What? | Who? | (By) When? | Status by 13 Jun 2019 |
| --- | --- | --- | --- | --- |
|  | For next meeting/call |  |  |  |
| 190228 190516 | Membership: Ensure signature of by-laws and governance rules by remaining Members | N. Francis | Sep 2019 | On-going |
| 190228 190516 | Membership: Participate in events in Asia only when travel and accommodation costs are sponsored | C. Braibant | China: Jun 2019 Japan: Oct-Nov 2019 | Done (China, i2a not going, Campine will) On-going (Japan) |
| 190516 | Communication: Circulate word document with i2a website content to Communication Task Force for comments | N. Francis | May 2019 | On-going |
| 190516 | Communication: Like and share LinkedIn and Twitter posts from i2a | Members | Every Friday |  |
| 190228 190615 | Regulatory: Inform i2a about cases of deviations from i2a’s self-classifications for Sb substances on the market | Members | ASAP |  |
| 190228 190616 | Regulatory: - Chase NTP to obtain clarification on scope and timing of RoC Listing of ATO - Collect feed-back from Dr Olden on solutions left to i2a to obtain recognition for limited scope of RoC Listing | C. Braibant | Sep 2019 | On-going Done |
| 190516 | Regulatory: Update responses to REACH Draft Decisions with extended research timeframe | C. Braibant | May 2019 | Done |
| 190516 | Regulatory: Inform Secretariat about examples of unjustified deviations from i2a self-classifications so as to bring these to the attention of ECHA and REACH/CLP enforcement authorities (and address this anti-competitive behavior) | Members | Sep 2019 |  |
| 190228 190516 | Regulatory: Send all recent, reliable and relevant data for risk assessment to Environment Canada and Health Canada | C. Braibant | Jun 2019 | Done |
| 190228 190516 | Regulatory: Produce comment to draft TLV proposal from ACGIH (and include request for clarification of TLV calculation, and note on LoD/LoQ / sample duration vs activity duration) | C. Braibant, C. Boreiko | 31 May 2019 | Done |
| 190228 190516 | Regulatory: - Mobilize attention of Commission on RoHS project to avoid useless/damaging results - Respond to remaining RoHS stakeholder consultations regarding Annex II - Monitor RoHS Review and participate in consultation | C. Braibant (with BSEF, EM and cefic) | Sep 2019 | On-going |
| 190516 | Regulatory: Find out whether it is recommended or not to request the non-nomination of Sb for ATSDR Toxicity Profile development/update | C. Braibant | < 20 May 2019 | Done |
| 190516 | Regulatory: Prepare a letter to be sent by an Oekotex-certified Member to Oekotex to: - Request removal of recent statement on Oekotex website - Request justification for such a statement - Inform Oekotex about on-going Evaluation of Sb trioxide |  |  |  |
| 171130 180405 180626 190615 | Regulatory: - Commission SEA study to quantify societal value of Sb substances - Circulate draft Roskill report for comment to the GA and include comments already collected on 16 May - Compile final report with all comments received - Announce conclusions of final report in a dedicated Press Release - Send final report to all EU authorities inspecting Sb substances - Use SEA report to update volume/use information in REACH Dossiers - Subsequently, use SEA to determine: - Relative value/benefits of Sb vs other metals - Costs triggered by a reclassification (or RoHS restriction) - Quantification of trade-off between chemical risk and fire safety | C. Braibant | Nov 2018 Jun 2019 Jul 2019 Sep 2019 Sep 2019 2020 2020 | Done Done |
| 181115 | Budget: Revise LoA itemization/fee justification and reimbursement/reinvoicing calculations upon final 2018 expenses | C. Braibant / Treasurer / Board | Sep 2019 |  |
| 190516 | Budget: Prepare budget and cost-sharing prediction for REACH Evaluation | C. Braibant /Treasurer / Board | Sep 2019 |  |
| 181115 190516 | Budget: - Based on revised LoA itemization/fee justification and reimbursement/reinvoicing calculations upon final 2018 expenses, and REACH Evaluation budget and cost-sharing predictions, prepare communication to inform about cost implications of retaining active REACH registrations for the evaluated Sb substances - Send agreed communication to all registrants | C. Braibant /Treasurer / Board | Sep 2019 |  |
|  | For End 2019 |  |  |  |
| 181115 | Agree on which/how workplace exposure data collected during i2a’s Workplace Exposure Monitoring Campaign will be reported to authorities | C. Braibant/EHS Group/Board | End 2019 |  |
| 190228 | Check success of Associate Association membership and decide whether to retain or adjust | Board | End 2019 |  |