## Slide 1: i2a EHS CONFERENCE CALL
15. October 2019

## Slide 2: Agenda
Welcome and introduction
i2a research strategy overview
Zoom on Reproductive Toxicity assessment
Update on carcinogenicity assessment
AOB and next meetings/calls

## Slide 3: 1. Welcome and introduction

## Slide 4: Participants
Members : Steven Verbeckmoes (Umicore), Marie-Laure Ledrich Traxys), Rien Repriels (Campine), Mari Carmen Belles (ITACA), Peter Faullant and Hubert Untersteiner (Tribotecc), Daisy Li and Joel Tenney (ICL-group), Oliver Schmid (Basf), Abulikemu Mubalake (Recylex)
I2a : Marjorie Huppert.
External : Craig Boreiko, Lindsay Aveyard.

## Slide 5: 2. i2a research overview reminder

## Slide 6: Overview of the research strategy
Lung toxicity and Carcinogenicity/Genotoxicity
Systemic and Reproductive toxicity
2020-2021
In vivo Combined oral screening reproductive toxicity
2022
In vivo Oral PNDT study
2023 …..
In vivo 90 days oral repeated study
2019-2020
In vivo DRFs
2019
In vitro Bioelution gastric assay
2021 -2022?
In vivo 90 days dose inhalation study
2019-2020
Comparative in vitro lung assay lung cells
+ In vitro Micro Nucleus Assay
2018-2019
In Vitro Toxtracker Assay

## Slide 7: 3. Zoom on Reproductive toxicity assessment

## Slide 8: Reproductive data
No effects on reproductive function and reproductive organs
Maternal toxicity at high exposure
Delayed fetal ossification
Available Data
Data Gaps
MoA behind maternal toxicity
Influence of maternal toxicity on miscarriages and delayed ossification
(Ir)reversibility of delayed ossification
Comparative data for all 10 Sb substances
Miscarriages at high exposure

## Slide 9: Stepwise approach Tier 1: Bioelution in simulated gastric fluids
  Principle:
    Bioelution studies measure the degree to which Sb is dissolved in the simulated gastric fluid, a route for assessing systemic toxicity and reproductive toxicity
  Results:
    Most soluble substances are the Sb 5+ compounds (except APO)
    Least soluble substances are Sb and Sb 3+ compounds
    Will advocate the choice of the substance for further in vivo testing
    Reinforce the read across approach

## Slide 10: Stepwise approach Tier 2: Dose Range Finding Studies (1)
10 substances
Oral dietary or gavage exposure
18 males and females /subst
3 treatment intensities
2 weeks

## Slide 11: Stepwise approach Tier 2: Dose Range Finding Studies What does it involve?
The study consist in:
  Weekly Clinical observation, twice weekly bodyweight of the animals and twice weekly food (containing Sb item) and water consumption tracking at Day-3 to Day 15
  Macroscopy examination with weights (liver, spleen, kidneys, tissue retention);
  Blood sampling at Day15, if diet administration

## Slide 12: Stepwise approach Tier 2: Dose Range Finding Studies (2) Blood sampling
For now only 1 blood sample is planed to be collected at the end of the study.
But should we plan to collect more samples ?
Current proposal
1 sample
Cost effective : 6000 €
Time efficient
Ratio Sb blood level/ Sb absorbed
Limits data on TK
Limits possibility of adjustments for futher studies
Option 2
2 times 6 samples
Day 1 and D14
Sb TK
Identification of Cmax
Identification of potential accumulation
Adjustment of dietary regimens for further studies
Additional cost for sampling
6000x12= 72 000 €
Additional cost for number of sample analysis (200 to 1500 sampls)
Option 3
?
?
?
FOR DISCUSSION

## Slide 13: Stepwise approach Tier 2: Dose Range Finding Studies (2) Blood sampling
Blood samples need to be analyzed:
TK analysis are generally done on serum but it depends on the properties of the analytics. Whole Blood, Red Bloods Cells, plasma have been also considered.
But what do we measure?
Option 1:
Sb total only
Cost effective
Time efficient
At Covance site
ICP-MS Method
Relation between all Sb species and effect
Quote estimated to100 000 € for 12 samples/animal to be confirmed, < 50 000 € for 1 sample/animal
No relation between effects and responsible ion
Option 2
Sb Total, Sb III, Sb V
Relation between each species and effects
Not feasible at Covance site
Significant additional cost to develop the method
Require HPLC ICP MS equipment
220 000 € for 12 samples/animal
70 000 € for 1 sample/animal
Option 3
?
?
?
FOR DISCUSSION

## Slide 14: Stepwise approach Tier 2: Dose Range Finding Studies (2) Urine sampling
Urines sampling are not planned in the current proposal ?
However, presence of Calcium in urine could add data on the effects of antimonates on the physiological calcium metabolism.?
Would it affect/explain effect on observed delayed ossification in foetus.?
A request for quoting the urine collection has been sent.
FOR DISCUSSION

## Slide 15: Stepwise approach Tier 2: Dose Range Finding Studies (2) Timing
The Covance proposal has been accepted by i2a
Samples will be requested to be sent to UK
Preliminary testing will define the adequate dose
The study is planned to start Q1 2020
Q4 2019 is then dedicated for refinement of the technical details
  Decision of the entity to measure in blood
  Decision of the number of blood samples
  Decision to add urine collection

## Slide 16: 4. Update on Carcinogenicity/Genotoxicity

## Slide 17: In vitro inhalation study
- The IOM in vitro lung toxicity study has been accepted by i2a.
- Technical details for the phase 1 (Sb characterization and preparation of the respirable samples) have been clarified.
11 compounds in a powder form will be prepared to be tested in phase 2a.
3 samples in a liquid form will be pretested to be included adequately in phase 2a.
- Some comments, received in September, need to be shared with IOM to finalize the set-up of phase 2a (determination of cytotoxicity, oxidative potential and inflammation in rats and human in vitro models)
14 samples should be tested
-Phase 2b, will be designed following results of phase 2a

## Slide 18: Invalidation of false positive genotoxicity assays
Equivocal results in micronucleus assays from the available literature could be due to inappropriate staining methods.
i2a is launching an in vitro micronucleus study on CHO WBL cells
Most of the positive reported in vitro MN studies utilized ATC, which makes the compound eligible to be tested for establishment of the validity or invalidity of reported assays
The method to staining and restaining and the identification of the dose is on clarification between Craig and ILS
Method to measure the content of Sb in media cells is also on discussion.
Samples were planned to be shipped in October to start the test by end of the month.

## Slide 19: 5. AOB

## Slide 20: AOB
Substance Evaluation
  REACH Evaluation updated decisions will be sent to Member State Committee by end Oct. Echa will inform registrants on the proposals for amendments (PfAs) and Registrants will have 30-45 days to comment the PfA. This may be before or after Christmas depending on whether the PfAs are sent before.
RoHS :
  i2a is preparing individual and collective responses to the various consultations (RoHS Substance Inventory and RoHS Review), and awaiting the publication of the restriction recommendation for ATO planned end Oct 2019.
US NTP RoC
  Informative Quality Act Petition (IQA) was submitted on 11 Oct. US NTP has 60 days to respond.

## Slide 21: AOB
Genotoxicity publication
  The second draft has been reviewed by i2a. Craig Boreiko and Toby Rossman, are finalizing it. The draft is intended to be sent by end of October to the selected Journal of publication: “Toxicology applied to Pharmacology”.
Toxtracker publication
  The fist draft has been shared with the EHS group on 26. September. Deadline to comment was last Friday. i2a needs to clarify some figures with Toxys and the first review will be sent to Craig by 18. October.

## Slide 22: AOB
Workplace Exposure Monitoring Campaign
  The monitoring campaign is on going and an update has been given at the Sb day 2019
  A presentation about a project aiming to study the observed variations between exposure datasets collected on various sites with different samplers, took place at the last GA. This shows how the scientific robustness of the exposure data is fragilized. Members showed a genuine interest.
  More information is available on request.

## Slide 23: AOB
Update on the EUROMETAUX bioelution gastric protocol
  The applicability of this Gastric Test is discussed by ECVAM on the fact that some substance may precipitate in gastric fluids making the results unreliable. APC and ATC have shown precipitates in our recent bioelution testing. The aim is to keep the applicability of this test for Sb and at minimum all compounds which do not precipitate in gastric fluids.
XLS EHS Tracking sheet.
  As informed in the last August EHS communication, the EHS tracking sheet is on review due to the significant evolvement of the i2a research strategy. The tool will be shared at the next EHS communication.
Next date:
  12. December 2019 - Call 14:00 CET time

## Slide 26: Minutes
Attendants
  Carr Smith (Albemarle), Peter Faullant and Hubert Untersteiner (Tribotecc), Rien Repriels (Campine), Isabelle Gaou (Arkema), Adriana Jalba and Daisy Li (ICL), Marie-Laure Ledrich (Traxys), Steven Verbeckmoes (Umicore), Craig Boreiko and Lindsay Aveyard (external).
  The participants had no comments on last august update.
  All actions are in progress and in-time
  The agenda was approved

## Slide 27: Minutes
Overview of the research strategy with bioelution results were reviewed to introduce the discussion on the Dose Range Finding study.
Maternal toxicity and miscarriages had been observed following high level exposure by injection to Sb(V) compounds used in the treatment of parasitic disease. These studies had defined the dose levels and reproductive impacts that required further dosimetric and mechanistic study.

## Slide 28: Minutes
The DRF was presented in details. Discussion on the number of blood samplings raise several comments:
  Collecting urines from the treated animals could be relevant, especially for the antimony V compounds. Analyzing urinary calcium would help identify the MoA for effects. Urinary Sb could be linked to estimated bioavailability and would help define the toxicokinetics and potential metabolism of the different Sb compounds to be tested.
  The number of animals has been commented to be quite low. The risk to observe a high variability in the results is present which can make more difficult the interpretation.
  One of the aim of the DRF is to identify the Maximum Tolerated Dose.

## Slide 29: Minutes
  Emetic properties of Sb and Sb compounds have been taken into account in case of dietary exposure.
  If dissolution of the products, gavage can be also problematic due to the corrosive and irritative properties of APC and ATC.
  Sampling at D7 and D8 could be considered in case of gavage but the number of sampling has been design with budget constraints, keeping focus on the objective of the study (identification of the dose and substance to use for further testings). Therefore, additional sampling are not essential.
  It was understood that the number of blood sampling will be determined when the type of exposure will be decided; This cannot be fixed at this moment as it requires preliminary testing to see how animals can absorb the preparation and the formulation method. If diet absorption is compatible with the properties of the compounds , members were not against to consider a diet exposure with one sampling at the end of the study.

## Slide 30: Minutes
The discussion continued with an exchange on the advantages and disadvantages of measuring Sb total or Sb total and Sb species
  It is anticipated that conversion of Sb(V) to Sb(III) and/or methylation of Sb compounds may occur after exposure and before analysis.
  Assessment of conversion can provide very valuable information.
  Blood and urine Sb measurements taken from exposed workers may have established the analytical techniques for assessing conversion.

## Slide 31: Minutes
  XRD analysis from human blood samples from site workers was suggested to be shared to determine a potential added value to measure the species. However, this suggestion was not retained as XRD and HPLC-ICP methods are not comparable. The XRD method is suitable for solid crystalline samples and not for biological samples.
  The pH evolution between absorption and measurment can also affect the conversion of the compounds’ valance, especially for the chloride compounds.
  The method to measure Sb needs to be clarified. → i2a to ask detailed method and quote from Covance to measure the Sb Total before final decison

## Slide 32: Minutes
The other i2a EHS topics were presented for information with confirmation of the date of the next EHS call;
Update of the i2a actions will be circulated to the EHS group in the meantime.